## SUMMARY
PHASE III & ENABLING - PILING & CIVIL WORKS DPR
| Date of Progress | 2024-07-03
| Date of Report | 2024-07-04
S.No. | Project Name | Piling Work (in Nos) | [10 empty] | Civil Work (in m3)
|  | Total estimated scope | Drg received | Clear Front | Monthly Plan | FTD (For the day) | MTD completed | % completed MTD | Completed till Last month | Cumulative completed till date | % completed as against scope |  | Total estimated scope | Drg received | Clear Front | Monthly Plan | FTD (For the day) | MTD completed | % completed MTD | Completed till Last month | Cumulative completed till date | % completed as against scope
1 | Rerouting of cable gallery for BF-3 | 622 | 622 | 622 |  | 0 | 0 | 0% | 622 | 622 | 100 |  | 3854 | 3854 | 3854 |  | 0 | 0 | 0% | 3782 | 3782 | 98.1318
2 | ARS Relocation | 56 | 56 | 56 |  | 0 | 0 | 0% | 56 | 56 | 100 |  | 525 | 525 | 525 |  | 0 | 0 | 0% | 505 | 505 | 96.1905
3 | Relocation of GAIL gas metering station | 60 | 60 | 60 | 58 | 4 | 12 | 20.69% | 2 | 14 | 23.3333 |  | 150 |  |  |  | 0 | 0 | 0% | 0 | 0 | 0
4 | BOF-III | 3500 | 836 | 599 | 200 | 0 | 2 | 1% | 436 | 438 | 12.5143 | [5 empty] | 0 | 0 | 0% | 0 | 0 | 0
5 | BF-III | 14725 | 5514 | 2333 | 661 | 9 | 30 | 4.539% | 1110 | 1140 | 7.7419 | Monthly plan 700 | 140403 | 12400 | 9805 |  | 0 | 0 | 0% | 0 | 0 | 0
6 | Flux Conveyor SP-III | 111 | 111 | 111 |  | 0 | 0 | 0% | 111 | 111 | 100 |  | 710 | 710 | 710 |  | 0 | 0 | 0% | 710 | 710 | 100
7 | RMHS-III | 8400 | 1349 | 1227 | 200 | 3 | 10 | 5% | 125 | 135 | 1.6071 |  | 119750 | 485 |  |  | 0 | 0 | 0% |  |  | 0
8 | CSP-II | 16600 | 1070 | 302 | 400 | 6 | 18 | 4.5% | 126 | 144
| Total | 44074 | 9618 | 5310 | 1519 | 22 | 72 | 4.74% | 2588 | 2660 | 6.035% |  | 265392 | 17974 | 14894 | 0 | 0 | 0 | 0% | 4997 | 4997 | 1.883%

## 02.07.2024
PHASE III & ENABLING - PILING & CIVIL WORKS DPR
| Date of Progress | 2024-07-02
| Date of Report | 2024-07-03
S.No. | Project Name | Piling Work (in Nos) | [10 empty] | Civil Work (in m3)
|  | Total estimated scope | Drg received | Clear Front | Monthly Plan | FTD (For the day) | MTD completed | % completed MTD | Completed till Last month | Cumulative completed till date | % completed as against scope |  | Total estimated scope | Drg received | Clear Front | Monthly Plan | FTD (For the day) | MTD completed | % completed MTD | Completed till Last month | Cumulative completed till date | % completed as against scope
1 | Rerouting of cable gallery for BF-3 | 622 | 622 | 622 |  | 0 | 0 | 0% | 622 | 622 | 100 |  | 3854 | 3854 | 3854 |  | 0 | 0 | 0% | 3782 | 3782 | 98.1318
2 | ARS Relocation | 56 | 56 | 56 |  | 0 | 0 | 0% | 56 | 56 | 100 |  | 525 | 525 | 525 |  | 0 | 0 | 0% | 505 | 505 | 96.1905
3 | Relocation of GAIL gas metering station | 60 | 60 | 60 | 58 | 6 | 8 | 13.79% | 2 | 10 | 16.6667 |  | 150 |  |  |  | 0 | 0 | 0% | 0 | 0 | 0
4 | BOF-III | 3500 | 836 | 599 | 200 | 0 | 2 | 1% | 436 | 438 | 12.5143 | [5 empty] | 0 | 0 | 0% | 0 | 0 | 0
5 | BF-III | 14725 | 5514 | 2333 | 661 | 10 | 21 | 3.177% | 1110 | 1131 | 7.6808 | Monthly plan 700 | 140403 | 12400 | 9805 |  | 0 | 0 | 0% | 0 | 0 | 0
6 | Flux Conveyor SP-III | 111 | 111 | 111 |  | 0 | 0 | 0% | 111 | 111 | 100 |  | 710 | 710 | 710 |  | 0 | 0 | 0% | 710 | 710 | 100
7 | RMHS-III | 8400 | 1349 | 1227 | 200 | 4 | 7 | 3.5% | 125 | 132 | 1.5714 |  | 119750 | 485 |  |  | 0 | 0 | 0% |  |  | 0
8 | CSP-II | 16600 | 1070 | 302 | 400 | 6 | 12 | 3% | 126 | 138
| Total | 44074 | 9618 | 5310 | 1519 | 26 | 50 | 3.292% | 2588 | 2638 | 5.985% |  | 265392 | 17974 | 14894 | 0 | 0 | 0 | 0% | 4997 | 4997 | 1.883%

## 01.07.2024
PHASE III & ENABLING - PILING & CIVIL WORKS DPR
| Date of Progress | 2024-07-01
| Date of Report | 2024-07-02
S.No. | Project Name | Piling Work (in Nos) | [10 empty] | Civil Work (in m3)
|  | Total estimated scope | Drg received | Clear Front | Monthly Plan | FTD (For the day) | MTD completed | % completed MTD | Completed till Last month | Cumulative completed till date | % completed as against scope |  | Total estimated scope | Drg received | Clear Front | Monthly Plan | FTD (For the day) | MTD completed | % completed MTD | Completed till Last month | Cumulative completed till date | % completed as against scope
1 | Rerouting of cable gallery for BF-3 | 622 | 622 | 622 |  | 0 | 0 | 0% | 622 | 622 | 100 |  | 3854 | 3854 | 3854 |  | 0 | 0 | 0% | 3782 | 3782 | 98.1318
2 | ARS Relocation | 56 | 56 | 56 |  | 0 | 0 | 0% | 56 | 56 | 100 |  | 525 | 525 | 525 |  | 0 | 0 | 0% | 505 | 505 | 96.1905
3 | Relocation of GAIL gas metering station | 40 | 40 | 10 |  | 0 | 0 | 0% | 0 | 0 | 0 |  | 150 |  |  |  | 0 | 0 | 0% | 0 | 0 | 0
4 | BOF-III | 3500 | 836 | 599 | 200 | 2 | 2 | 1% | 436 | 438 | 12.5143 | [5 empty] | 0 | 0 | 0% | 0 | 0 | 0
5 | BF-III | 14725 | 5514 | 2333 | 661 | 11 | 11 | 1.664% | 1110 | 1121 | 7.6129 | Monthly plan 700 | 140403 | 9805 | 9805 |  | 0 | 0 | 0% | 0 | 0 | 0
6 | Flux Conveyor SP-III | 111 | 111 | 111 |  | 0 | 0 | 0% | 111 | 111 | 100 |  | 710 | 710 | 710 |  | 0 | 0 | 0% | 710 | 710 | 100
7 | RMHS-III | 8400 | 1349 | 1227 | 200 | 3 | 3 | 1.5% | 125 | 128 | 1.5238 |  | 119750 | 485 |  |  | 0 | 0 | 0% |  |  | 0
8 | CSP-II | 16600 | 1070 | 302 | 400 | 6 | 6 | 1.5% | 126 | 132
| Total | 44054 | 9598 | 5260 | 1461 | 22 | 22 | 1.506% | 2586 | 2608 | 5.92% |  | 265392 | 15379 | 14894 | 0 | 0 | 0 | 0% | 4997 | 4997 | 1.883%